## May–Jun 2026 Plan
Date | Type | Title | Target Keyword | Est. Vol/mo | Difficulty | Format | Priority | Pillar | Why (1-liner)
2026-05-04 | Update Blog | Rewrite: /blog/remote-screen-monitoring-software-a-game-changer-for-work-from-home-teams | remote screen monitoring software |  | Medium Competition | 2200w blog | critical | SEO | 47K impressions but only 72 clicks at pos 35 — refresh to start capturing them
2026-05-04 | Update Blog | Refresh existing page targeting "workforce productivity platform" | workforce productivity platform | 364 |  | 1500w blog | high | SEO | Already ranking — push to top 10 for measurable click lift (364 monthly searches, KD per Moz)
2026-05-04 | Update Blog | Refresh existing page targeting "track remote employees" | track remote employees | 57 |  | 1500w blog | medium | SEO | Already ranking — push to top 10 for measurable click lift (57 monthly searches, KD per Moz)
2026-05-04 | Create Blog | Agentic AI in employee monitoring: the complete guide | agentic AI employee monitoring | 450 | Low Competition | 2500w guide | high | SEO | 450 monthly searches, very low competition — uncontested theme (Agentic AI)
2026-05-05 | Update Blog | Rewrite: /blog/best-work-from-home-monitoring-software | best work from home monitoring software |  | High Competition | 2500w listicle | critical | SEO | 51K impressions, 27 clicks (CTR 0.05%) at pos 43 — biggest impression/click gap on the site
2026-05-05 | Update Blog | Refresh existing page targeting "remote working monitoring software" | remote working monitoring software | 174 |  | 1500w blog | medium | SEO | Already ranking — push to top 10 for measurable click lift (174 monthly searches, KD per Moz)
2026-05-05 | Update Blog | Refresh existing page targeting "workforce analytics software" | workforce analytics software | 47 |  | 1500w blog | medium | SEO | Already ranking — push to top 10 for measurable click lift (47 monthly searches, KD per Moz)
2026-05-05 | Create Blog | How AI recommendations improve workforce productivity | AI workforce recommendations | 450 | Low Competition | 1500w guide | medium | SEO | 450 monthly searches, very low competition — uncontested theme (Agentic AI)
2026-05-06 | Ops | Set up Google Business Profile + request 25 customer reviews |  |  |  | External admin / report | medium | GEO | No GBP listing today — 'we360' branded SERP shows no knowledge panel; 25 reviews lift visibility 3-5×
2026-05-06 | Update Blog | Rewrite: /blog/top-5-prohance-alternatives-in-2025 | prohance alternative |  | Medium Competition | 1800w blog | critical | SEO | Already ranking #10 for 'prohance alternative' (16K imp/16mo) — push to top 5 with retitle + answer-capsule
2026-05-06 | Update Blog | Refresh existing page targeting "employee efficiency" | employee efficiency | 56 |  | 1500w blog | medium | SEO | Already ranking — push to top 10 for measurable click lift (56 monthly searches, KD per Moz)
2026-05-06 | Update Blog | Refresh existing page targeting "workforce analytics solution" | workforce analytics solution | 33 |  | 1500w blog | medium | SEO | Already ranking — push to top 10 for measurable click lift (33 monthly searches, KD per Moz)
2026-05-06 | Create Blog | Field employee GPS tracking software India: complete guide | field employee GPS tracking India | 750 | Low Competition | 2500w guide | high | GEO | 750 monthly searches, very low competition — uncontested theme (India Field Force GPS)
2026-05-07 | Update Blog | Rewrite: /blog/how-to-measure-productivity-formula-metrics-and-best-methods | how to measure productivity |  | Medium Competition | 2800w listicle | high | SEO | 29K imp, 53 clicks at pos 17.5 — striking distance + absorb 'what causes low productivity' (25K imp/16mo)
2026-05-07 | Update Blog | Refresh existing page targeting "user tracking software" | user tracking software | 30 |  | 1500w blog | medium | SEO | Already ranking — push to top 10 for measurable click lift (30 monthly searches, KD per Moz)
2026-05-07 | Update Blog | Refresh existing page targeting "user activity monitoring tools" | user activity monitoring tools | 35 |  | 1500w blog | medium | SEO | Already ranking — push to top 10 for measurable click lift (35 monthly searches, KD per Moz)
2026-05-07 | Create Blog | AI vs traditional employee monitoring: what's the difference? | AI vs traditional monitoring | 300 | Low Competition | 1500w comparison | medium | SEO | 300 monthly searches, very low competition — uncontested theme (Agentic AI)
2026-05-08 | Update Blog | Rewrite: /blog/team-dynamics-at-workplace | team dynamics at workplace |  | Low Competition | 2000w blog | medium | SEO | 22K imp, 101 clicks at pos 16 — already 100+ clicks/16mo, refresh to ~3× clicks
2026-05-08 | Update Blog | Refresh existing page targeting "productivity monitoring" | productivity monitoring | 27 |  | 1500w blog | medium | SEO | Already ranking — push to top 10 for measurable click lift (27 monthly searches, KD per Moz)
2026-05-08 | Update Blog | Refresh existing page targeting "employee spy software" | employee spy software | 20 |  | 1500w blog | medium | SEO | Already ranking — push to top 10 for measurable click lift (20 monthly searches, KD per Moz)
2026-05-08 | Create Blog | Live screen monitoring software: complete guide 2026 | live screen monitoring software | 900 | Low Competition | 2500w guide | high | SEO | 900 monthly searches, very low competition — uncontested theme (Livestream Monitoring)
2026-05-11 | Update Blog | Rewrite: /blog/zoho-people-vs-keka-hr | zoho people vs keka |  | Medium Competition | 1800w blog | high | SEO | Already top-10 (pos 10.6, 76 clicks/16mo) for 'zoho people vs keka' — small refresh pushes to top 5
2026-05-11 | Create Blog | When is live employee monitoring appropriate? Ethics guide | employee live monitoring ethics | 450 | Low Competition | 2000w guide | medium | SEO | 450 monthly searches, very low competition — uncontested theme (Livestream Monitoring)
2026-05-12 | Update Blog | Striking-distance refresh: /blog-generator ("blog generator") | blog generator |  | Medium Competition | 1500w blog | high | SEO | 4,346 imp/mo for 'blog generator' at pos 13 — striking distance for top 10 (~280 clicks/mo upside)
2026-05-12 | Create Blog | The future of workforce management: AI-driven insights 2026 | future of workforce management AI | 600 | Low Competition | 2000w blog | medium | SEO | 600 monthly searches, very low competition — uncontested theme (Agentic AI)
2026-05-13 | Update Blog | Striking-distance refresh: /automated-attendance ("cloud-based attendance system") | cloud based attendance system |  | Medium Competition | 2000w blog | high | SEO | Cluster of 4 attendance-system queries at pos 11–16 (~7K imp/16mo combined) — refresh for top 5
2026-05-13 | Create Blog | How FMCG companies in India track field sales teams | FMCG field force tracking India | 300 | Low Competition | 2000w guide | medium | GEO | 300 monthly searches, very low competition — uncontested theme (India Field Force GPS)
2026-05-13 | Create Blog | Livestream vs screenshot monitoring: which is right for your team? | livestream vs screenshot monitoring | 300 | Low Competition | 1500w comparison | medium | SEO | 300 monthly searches, very low competition — uncontested theme (Livestream Monitoring)
2026-05-14 | Update Blog | Striking-distance refresh: /job-descriptions/crm-specialist ("crm specialist") | crm specialist |  | Low Competition | 1500w blog | medium | SEO | Existing JD template at pos 17 — expand with salary + skills + interview Qs to push top 5
2026-05-15 | Update Blog | Refresh existing page targeting "measure of productivity" | measure of productivity | 246 |  | 1500w blog | low | SEO | Already ranking — push to top 10 for measurable click lift (246 monthly searches, KD per Moz)
2026-05-15 | Update Blog | Refresh existing page targeting "workforce tracking" | workforce tracking | 25 |  | 1500w blog | low | SEO | Already ranking — push to top 10 for measurable click lift (25 monthly searches, KD per Moz)
2026-05-18 | Update Blog | Refresh existing page targeting "formula for constant workforce planning" | formula for constant workforce planning | 27 |  | 1500w blog | low | SEO | Already ranking — push to top 10 for measurable click lift (27 monthly searches, KD per Moz)
2026-05-18 | Update Blog | Refresh existing page targeting "pc monitoring tools" | pc monitoring tools | 25 |  | 1500w blog | low | SEO | Already ranking — push to top 10 for measurable click lift (25 monthly searches, KD per Moz)
2026-05-18 | Update Page | Retarget homepage to rank for "employee monitoring software" | employee monitoring software | 10000 | High Competition | 0w landing page | critical | SEO | 'Employee monitoring software' = 10K monthly searches — biggest keyword gap (we're not in top 50 today)
2026-05-19 | Update Blog | Refresh existing page targeting "remote screen monitoring software" | remote screen monitoring software | 22 |  | 1500w blog | low | SEO | Already ranking — push to top 10 for measurable click lift (22 monthly searches, KD per Moz)
2026-05-19 | Create Blog | How we360.ai's AI engine detects productivity risks | AI productivity risk detection | 225 | Low Competition | 1200w guide | medium | SEO | 225 monthly searches, very low competition — uncontested theme (Agentic AI)
2026-05-19 | Create Blog | Real-time monitoring for BPO and call centre teams India | real time monitoring BPO India | 250 | Low Competition | 2000w blog | medium | SEO | 250 monthly searches, very low competition — uncontested theme (Livestream Monitoring)
2026-05-20 | Update Blog | Refresh existing page targeting "tracking remote worker engagement" | tracking remote worker engagement | 28 |  | 1500w blog | low | SEO | Already ranking — push to top 10 for measurable click lift (28 monthly searches, KD per Moz)
2026-05-20 | Update Blog | Refresh existing page targeting "softwar for tracking people" | softwar for tracking people | 27 |  | 1500w blog | low | SEO | Already ranking — push to top 10 for measurable click lift (27 monthly searches, KD per Moz)
2026-05-20 | Create Blog | How to calculate the real cost of unproductive employees | cost of unproductive employees | 750 | Low Competition | 2500w guide | medium | SEO | 750 monthly searches, very low competition — uncontested theme (Cost Intelligence)
2026-05-21 | Update Blog | Refresh existing page targeting "pc monitoring tools with notifications" | pc monitoring tools with notifications | 27 |  | 1500w blog | low | SEO | Already ranking — push to top 10 for measurable click lift (27 monthly searches, KD per Moz)
2026-05-21 | Create Blog | GPS attendance for field staff: legal and practical guide India | GPS attendance field staff India | 600 | Low Competition | 2000w guide | medium | GEO | 600 monthly searches, very low competition — uncontested theme (India Field Force GPS)
2026-05-22 | Update Blog | Refresh existing page targeting "maximum productivity" | maximum productivity | 20 |  | 1500w blog | low | SEO | Already ranking — push to top 10 for measurable click lift (20 monthly searches, KD per Moz)
2026-05-25 | Create Page | Build /features/remote-employee-monitoring (new feature pillar) | remote employee monitoring software | 3000 | High Competition | 3000w landing page | critical | SEO | 3K monthly searches for 'remote employee monitoring software' — dedicated feature page (we don't have one)
2026-05-26 | Create Blog | Employee monitoring ROI: complete guide for CFOs | employee monitoring ROI | 450 | Low Competition | 2000w guide | medium | SEO | 450 monthly searches, very low competition — uncontested theme (Cost Intelligence)
2026-05-28 | Create Blog | Field force management software India: top options compared | field force management software India | 750 | Low Competition | 2000w blog | medium | GEO | 750 monthly searches, very low competition — uncontested theme (India Field Force GPS)
2026-05-30 | Create Blog | Publish industry-leader expertise blog (May) | industry expertise we360 may | 0 |  | 1500w blog | medium | AEO | Industry-leader byline — E-E-A-T signal + LinkedIn distribution drives referral traffic
2026-06-01 | Update Page | Refresh /features/screen-recording (target screen-monitoring head term) | screen monitoring software employees | 1750 | Medium Competition | 2500w landing page | high | SEO | Existing /features/screen-recording is thin — refresh for 'screen monitoring software' (1.7K vol, KD Medium)
2026-06-01 | Create Blog | Prune 41 thin/duplicate blog posts — execute keep/merge/410 decisions | blog pruning audit |  |  | 0w blog | high | SEO | Audit 41 thin blog posts (Crawled-not-indexed by Google) — decide merge, delete, or refresh each
2026-06-02 | Update Blog | Solution-page refresh: /solutions/employee-monitoring | employee monitoring software |  | High Competition | 2500w blog | critical | SEO | /solutions/employee-monitoring is our top BoF page — 393 sessions/mo today; refresh targets 1,000+ sessions/mo
2026-06-02 | Create Blog | Employee cost calculator (free tool) | employee cost calculator | 900 | Low Competition | 800w blog | medium | SEO | 900 monthly searches, very low competition — uncontested theme (Cost Intelligence)
2026-06-02 | Create Blog | Write "Best Employee Monitoring Software 2026" listicle | best employee monitoring software | 5500 | High Competition | 3500w listicle | critical | SEO | 5,500 monthly searches for 'best employee monitoring software 2026' — listicle owns this query type
2026-06-03 | Update Blog | Solution-page refresh: /attendance-tracking-software | attendance tracking software |  | High Competition | 2200w blog | high | SEO | /attendance-tracking-software has 75K imp/16mo at pos 35 — biggest latent-demand solution page
2026-06-03 | Create Blog | Shadow IT in Indian companies: what your employees are actually using | shadow IT India | 450 | Low Competition | 2000w blog | medium | SEO | 450 monthly searches, very low competition — uncontested theme (SaaS / Technology Usage)
2026-06-03 | Create Blog | Write blog: "How to track employee internet usage" | how to track employee internet usage | 2250 | Low Competition | 2500w guide | high | SEO | 2250 monthly searches — feature cluster blog feeding the relevant feature pillar
2026-06-04 | Update Blog | Solution-page refresh: /remote-employee-monitoring | remote employee monitoring |  | High Competition | 2200w blog | high | SEO | /remote-employee-monitoring has 82K imp/16mo at pos 39 — invisible to searchers despite high impressions
2026-06-04 | Create Blog | How to manage remote field employees across multiple cities | manage field employees multiple cities India | 300 | Low Competition | 1800w guide | medium | GEO | 300 monthly searches, very low competition — uncontested theme (India Field Force GPS)
2026-06-04 | Create Blog | Write blog: "Website monitoring for employees" | website monitoring for employees | 1500 | Medium Competition | 1800w blog | medium | SEO | 1500 monthly searches — feature cluster blog feeding the relevant feature pillar
2026-06-05 | Create Blog | Live monitoring compliance guide: Indian IT law, GDPR, PDPA | employee monitoring compliance India | 450 | Low Competition | 2500w guide | medium | SEO | 450 monthly searches, very low competition — uncontested theme (Livestream Monitoring)
2026-06-05 | Create Blog | Write blog: "Application usage tracking software" | application usage tracking software | 1150 | Medium Competition | 1800w blog | medium | SEO | 1150 monthly searches — feature cluster blog feeding the relevant feature pillar
2026-06-08 | Update Page | Refresh /features/productivity-tracking (target productivity-monitoring head term) | productivity monitoring software | 1750 | Medium Competition | 2500w landing page | high | SEO | Existing /features/productivity-tracking is thin — target 'productivity monitoring software' head term
2026-06-08 | Create Page | Build /vs/we360-vs-hubstaff (Hubstaff vs-page) | we360 vs hubstaff |  | Medium Competition | 2200w landing page | critical | SEO | Build /vs/we360-vs-hubstaff comparison page — captures evaluator-stage buyers comparing tools
2026-06-08 | Create Blog | How to compare employee productivity across multiple office locations | compare productivity multiple offices | 600 | Low Competition | 2000w guide | high | GEO | 600 monthly searches, very low competition — uncontested theme (Multi-Location Productivity)
2026-06-09 | Create Page | Build /vs/we360-vs-time-doctor (Time Doctor vs-page) | we360 vs time doctor |  | Medium Competition | 2200w landing page | critical | SEO | Build /vs/we360-vs-time-doctor comparison page — captures evaluator-stage buyers comparing tools
2026-06-09 | Create Blog | Workforce cost optimisation strategies for Indian companies | workforce cost optimisation India | 300 | Low Competition | 2000w blog | medium | SEO | 300 monthly searches, very low competition — uncontested theme (Cost Intelligence)
2026-06-09 | Create Blog | Write "How to Monitor Remote Employees" guide | how to monitor remote employees | 2250 | Low Competition | 2200w guide | high | SEO | 2,250 monthly searches, low competition — quick-win how-to guide
2026-06-10 | Create Page | Build /vs/we360-vs-teramind (Teramind vs-page) | we360 vs teramind |  | Medium Competition | 2200w landing page | high | SEO | Build /vs/we360-vs-teramind comparison page — captures evaluator-stage buyers comparing tools
2026-06-10 | Create Blog | How to reduce SaaS costs by tracking tool usage | reduce SaaS costs employee monitoring | 600 | Low Competition | 1800w guide | medium | SEO | 600 monthly searches, very low competition — uncontested theme (SaaS / Technology Usage)
2026-06-10 | Create Blog | Write blog: "How to track employee productivity" | how to track employee productivity | 5500 | High Competition | 2500w guide | high | SEO | 5500 monthly searches — feature cluster blog feeding the relevant feature pillar
2026-06-11 | Create Page | Build /vs/we360-vs-activtrak (ActivTrak vs-page) | we360 vs activtrak |  | Medium Competition | 2200w landing page | critical | SEO | Build /vs/we360-vs-activtrak comparison page — captures evaluator-stage buyers comparing tools
2026-06-11 | Create Blog | Multi-city workforce analytics for Indian enterprises | multi city workforce analytics India | 250 | Low Competition | 2000w blog | medium | GEO | 250 monthly searches, very low competition — uncontested theme (Multi-Location Productivity)
2026-06-11 | Create Blog | Write blog: "Employee productivity benchmarks India" | employee productivity benchmarks India | 450 | Low Competition | 1800w blog | medium | SEO | 450 monthly searches — feature cluster blog feeding the relevant feature pillar
2026-06-12 | Create Page | Build /vs/we360-vs-desktime (DeskTime vs-page) | we360 vs desktime |  | Medium Competition | 2200w landing page | high | SEO | Build /vs/we360-vs-desktime comparison page — captures evaluator-stage buyers comparing tools
2026-06-12 | Create Page | Build /solutions/time-tracking landing (target head term) | time tracking software for employees | 6500 | High Competition | 3000w landing page | high | SEO | 6,500 monthly searches for 'time tracking software for employees' — current /solutions/time-tracker is thin
2026-06-15 | Ops | Internal linking sweep — every BoF page gets 5+ internal links |  |  |  | External admin / report | high | SEO | BoF pages need ≥5 internal links each — cheapest CTR + topical-authority lift in the entire plan
2026-06-15 | Update Blog | Striking-distance refresh: /blog/canva-alternative ("canva alternatives") | canva alternatives |  | Medium Competition | 1800w blog | high | SEO | 1,020 imp/mo at pos 12 — refresh existing /blog/canva-alternative to top 5
2026-06-15 | Create Page | Build /vs/keka-vs-zoho (Zoho vs-page) | keka vs zoho |  | Medium Competition | 2200w landing page | high | SEO | Build /vs/keka-vs-zoho comparison page — captures evaluator-stage buyers comparing tools
2026-06-15 | Create Page | Build /features/livestream (new feature pillar — Hubstaff differentiator) | live screen monitoring software | 900 | Low Competition | 2500w landing page | high | SEO | Build /features/livestream — Hubstaff differentiator (they refuse to offer this); anchors livestream cluster
2026-06-15 | Create Page | Build /in/wfh-tracking-software-india (India BoF) | WFH tracking software India | 550 | Low Competition | 1800w landing page | high | GEO | 550 monthly searches for 'WFH tracking software India' — uncontested by global competitors
2026-06-15 | Create Page | Build /reviews/ (aggregate G2 + Capterra + Trustpilot reviews) | we360 reviews | 100 |  | 1200w landing page | medium | AEO | Aggregate G2/Capterra reviews on-site — strong AI Overview citation signal + branded SERP improvement
2026-06-16 | Create Page | Build /vs/zoho-vs-keka (Keka vs-page) | zoho vs keka |  | Medium Competition | 2200w landing page | high | SEO | Build /vs/zoho-vs-keka comparison page — captures evaluator-stage buyers comparing tools
2026-06-16 | Create Blog | New blog: "AI employee monitoring software" (924 imp/16mo) | ai employee monitoring software |  | Medium Competition | 2200w blog | high | SEO | —
2026-06-16 | Create Blog | How we360.ai's Cost Intelligence pays for itself | cost intelligence employee monitoring | 225 | Low Competition | 1500w guide | medium | SEO | 225 monthly searches, very low competition — uncontested theme (Cost Intelligence)
2026-06-17 | Update Blog | Striking-distance refresh: /professional-invoice-generator ("ai invoice generator") | ai invoice generator |  | Medium Competition | 1500w blog | medium | SEO | Existing /professional-invoice-generator at pos 12 for 'ai invoice generator' (894 imp/mo) — retitle for AI angle
2026-06-17 | Create Blog | Technology adoption analytics: are employees using your tools? | technology adoption analytics HR | 300 | Low Competition | 1500w blog | medium | SEO | 300 monthly searches, very low competition — uncontested theme (SaaS / Technology Usage)
2026-06-17 | Create Blog | Write blog: "How to block distracting websites at work" | how to block distracting websites at work | 1500 | Low Competition | 1800w guide | medium | SEO | 1500 monthly searches — feature cluster blog feeding the relevant feature pillar
2026-06-18 | Create Blog | Office vs WFH productivity in India: 2026 data and insights | office vs WFH productivity India | 1100 | Low Competition | 2500w comparison | medium | GEO | 1100 monthly searches, very low competition — uncontested theme (Multi-Location Productivity)
2026-06-18 | Create Blog | Write blog: "Idle time tracking for remote employees" | idle time tracking for remote employees | 600 | Low Competition | 1800w blog | medium | SEO | 600 monthly searches — feature cluster blog feeding the relevant feature pillar
2026-06-19 | Create Page | Build /in/leave-management-software-india | leave management software India | 1150 | Medium Competition | 1800w landing page | medium | GEO | 1,150 monthly searches for 'leave management software India' — overlaps with Keka/Zoho integration plays
2026-06-20 | Create Page | Build /how-it-works/ (explainer page — installation → tracking → reports) | how does we360 work | 200 |  | 1500w landing page | medium | AEO | Mid-funnel explainer covering install → tracking → reports — pre-sales education + branded SERP
2026-06-22 | Update Page | Refresh /features/agentic-ai (anchor for AI cluster) | AI-powered employee monitoring software | 1150 | Medium Competition | 2500w landing page | high | SEO | Refresh /features/agentic-ai to anchor the 5 Agentic AI cluster blogs (1,150 vol/mo for AI head term)
2026-06-22 | Create Page | Build /integrations/microsoft-teams (Microsoft Teams integration page) | microsoft teams employee monitoring integration |  | Low Competition | 1500w landing page | high | SEO | Build /integrations/microsoft-teams page — convert microsoft teams-shop visitors who can integrate We360
2026-06-23 | Create Page | Build /integrations/jira (Jira integration page) | jira employee monitoring integration |  | Low Competition | 1500w landing page | high | SEO | Build /integrations/jira page — convert jira-shop visitors who can integrate We360
2026-06-23 | Create Page | Build /in/field-force-management-india | field force management software India | 750 | Low Competition | 2000w landing page | high | GEO | 750 monthly searches — pillar for the 5 India Field Force cluster blogs (FMCG/pharma/insurance verticals)
2026-06-24 | Create Page | Build /integrations/keka (Keka integration page) | keka employee monitoring integration |  | Low Competition | 1500w landing page | high | SEO | Build /integrations/keka page — convert keka-shop visitors who can integrate We360
2026-06-24 | Create Blog | SaaS stack optimisation: the CFO's guide to software ROI | SaaS stack optimisation | 750 | Low Competition | 2500w guide | medium | SEO | 750 monthly searches, very low competition — uncontested theme (SaaS / Technology Usage)
2026-06-25 | Create Page | Build /integrations/zoho (Zoho People integration page) | zoho people employee monitoring integration |  | Low Competition | 1500w landing page | high | SEO | Build /integrations/zoho page — convert zoho-shop visitors who can integrate We360
2026-06-25 | Create Blog | Location performance analytics: what Indian HR leaders need to know | location performance analytics India | 225 | Low Competition | 1800w blog | medium | GEO | 225 monthly searches, very low competition — uncontested theme (Multi-Location Productivity)
2026-06-26 | Create Page | Build /integrations/greythr (greytHR integration page) | greythr employee monitoring integration |  | Low Competition | 1500w landing page | medium | SEO | Build /integrations/greythr page — convert greythr-shop visitors who can integrate We360
2026-06-26 | Create Blog | Write blog: "Project management + time tracking software" | project management time tracking software | 3000 | High Competition | 2500w blog | high | SEO | 3000 monthly searches — feature cluster blog feeding the relevant feature pillar
2026-06-30 | Create Blog | Publish industry-leader expertise blog (June) | industry expertise we360 jun | 0 |  | 1500w blog | medium | AEO | Industry-leader byline — E-E-A-T signal + LinkedIn distribution drives referral traffic